## Summary
Project Cost Plan - Residential House Template
Reusable residential house cost framework
02-skills/systems/Cost_Plan_vNN.xlsx
All figures exclude GST ¦ Framework adapted from L09-House-Price.xlsx
2026-05-30
Cost Code | Category | Cost Items | Budget | Approved Contract | Forecast | Approved Variations | Forecast Final Cost | Budget Variance | Claimed to Date | This Month | Remaining
1.1 | Fees and charges | AUTHORITIES FEES | 3788.13 | 0
1.3 | Fees and charges | HOW & LSL | 10011.48 | 0
SUBTOTAL - Fees and charges
1.2 | Consultants | CONSULTANTS | 1352.9 | 0
2.1 | Consultants | SURVEYORS | 4230.34 | 0
SUBTOTAL - Consultants
1.4 | Construction | TEMP SERVICES (SITE AMMENITIES) | 3246.97 | 0
1.5 | Construction | SUPERVISION | 16234.84 | 0
2.2 | Construction | EARTHWORKS | 10293.76 | 0
2.3 | Construction | TERMITE TREATMENT | 979.69 | 0
3.1 | Construction | FOUNDATION PIERS | 18083.2 | 0
3.2 | Construction | CONCRETE WORKS | 35427.81 | 0
4.1 | Construction | WALL FRAMING & ROOF TRUSSES | 58566.18 | 0
4.2 | Construction | STRUCTURAL STEEL | 7754.19 | 0
4.3 | Construction | MOBILE CRANE HIRE | 4041.96 | 0
4.4 | Construction | WINDOW SUPPLY | 19710.84 | 0
4.5 | Construction | MASONRY | 31879.77 | 0
4.6 | Construction | SCAFFOLDING | 16899.88 | 0
4.7 | Construction | ROOF RAIL PROTECTION | 2042.56 | 0
4.8 | Construction | ROOFING | 19428.33 | 0
4.9 | Construction | EXTERNAL CLADDING & EAVES SOFFIT | 29208.28 | 0
4.1 | Construction | LOCKUP | 8737.73 | 0
5.1 | Construction | INSULATION | 3816.14 | 0
5.2 | Construction | PLASTERBOARD | 18088.66 | 0
5.3 | Construction | WATERPROOFING | 4110.32 | 0
5.4 | Construction | GARAGE DOORS | 3330.11 | 0
5.5 | Construction | TILING | 26538.54 | 0
5.6 | Construction | JOINERY | 16864.59 | 0
5.7 | Construction | STONEWORK | 6347.76 | 0
5.8 | Construction | TAPWARE, FIXTURES & FITTINGS | 9038.61 | 0
5.9 | Construction | SHOWER SCREENS, MIRRORS & WARDROBES | 6856.54 | 0
5.1 | Construction | FIXOUT CARPENTRY | 3594.45 | 0
5.11 | Construction | APPLIANCES | 6117.53 | 0
5.12 | Construction | CARPET & FLOOR COVERING | 5414.59 | 0
5.13 | Construction | HYDRAULIC SERVICES | 16789.11 | 0
5.14 | Construction | HOT WATER SYSTEM | 1377.27 | 0
5.15 | Construction | ELECTRICAL SERVICES | 18282.72 | 0
5.16 | Construction | MECHANICAL SERVICES | 13279.32 | 0
5.17 | Construction | JOINT SEALING & CAULKING | 1794.56 | 0
6.1 | Construction | PAINTING | 17754.8 | 0
6.2 | Construction | SOFTSCAPE | 14066.41 | 0
6.3 | Construction | HARDSCAPE | 24879.09 | 0
6.4 | Construction | FENCING & GATES | 11405.38 | 0
6.5 | Construction | CLEANING | 9496 | 0
SUBTOTAL - Construction
4.99 | Contingency / allowances | Construction contingency |  | 0
SUBTOTAL - Contingency / allowances
GRAND TOTAL - HOUSE COST FRAMEWORK
Formulas:
This Month = SUMIFS(Invoices!$F5:F500,Invoices!$A5:A500,">="&K5,Invoices!$A5:A500,"<"&EDATE(K5,1),Invoices!$E5:E500,[Cost Items])

## Invoices
INVOICES REGISTER
Reusable residential house cost framework
Date | Company | PO Number | Invoice Number | Cost Item | Amount | Current Month | Paid?

## Variations
VARIATIONS REGISTER
Reusable residential house cost framework
Date Submitted | Cost Item | Variation To | Status | Amount | Date Approved | Approved Amount